## Summary
COMMON SETTINGS - TEST AUTOMATION REPORT
Generated: 23-May-2026 17:08
Total Tests |  | Passed |  | Failed |  | Skipped |  | Pass Rate | Duration
1 |  | 1 |  | 0 |  | 0 |  | 100% | 3m 49s
# | Module | Tests | Passed | Failed | Skipped | Duration | Status
1 | Customer | 1 | 1 | 0 | 0 | 3m 49s | PASS

## Test Results
TEST RESULTS
Detailed results per test case
# | Test Name | Module | Status | Duration | Timestamp | Steps | Error
1 | test_CU_D03_duplicate_email_create | Customer | PASSED | 3m 49s | 2026-05-23 17:04 | -

## Step Details
STEP DETAILS
Step-level results (auto-parsed from test logs)
# | Test Name | Step | Status | Detail
No step details captured

## Known Issues
KNOWN ISSUES / BUGS
4 issue(s) documented during testing
# | Severity | Module | Category | Description | Expected Behavior | Actual Behavior | Test Ref | Status
1 | Critical | Customer | Automation | Browser-clicked mat-select options do NOT update Angular reactive form model. Submit still fires 'Validation Failed' even with all fields filled via UI clicks. Must use JS value-setter + dispatchEvent pattern for all dropdown selections. | Selenium clicks on mat-select options should update form state. | CONFIRMED: Angular form model not synced. Need JS workaround. | ALL | Confirmed
2 | Medium | Customer | Validation | The horizontal stepper allows clicking Next to advance to the next step even when required fields on the current step are empty. No per-step validation is performed — validation only triggers on Submit. | Stepper should block advancement when required fields are empty. | CONFIRMED: Next button always works regardless of field state. | CU-C15 | Confirmed
3 | Medium | Customer | UI Bug | The Address grid column header shows 'Pin Code *' with an asterisk suggesting the field is required, but the HTML input element has required=false and the form does not validate it as required on submit. | Column header and field required attribute should match. | CONFIRMED: Header says required, but field is optional. | CU-C12 | Confirmed
4 | Medium | Customer | UI Bug | Bank Details grid column headers show asterisks for Bank Name, Branch, Account Holder Name, and Account Number, suggesting they are required. However, the HTML input elements have required=false. | Column headers and field required attributes should match. | CONFIRMED: Headers say required, but fields are optional. | CU-C13 | Confirmed