## Summary
COMMON SETTINGS - TEST AUTOMATION REPORT
Generated: 22-May-2026 18:17
Total Tests |  | Passed |  | Failed |  | Skipped |  | Pass Rate | Duration
1 |  | 1 |  | 0 |  | 0 |  | 100% | 3m 50s
# | Module | Tests | Passed | Failed | Skipped | Duration | Status
1 | Supplier | 1 | 1 | 0 | 0 | 3m 50s | PASS

## Test Results
TEST RESULTS
Detailed results per test case
# | Test Name | Module | Status | Duration | Timestamp | Steps | Error
1 | test_SP_C02_valid_create | Supplier | PASSED | 3m 50s | 2026-05-22 18:13 | -

## Step Details
STEP DETAILS
Step-level results (auto-parsed from test logs)
# | Test Name | Step | Status | Detail
No step details captured

## Known Issues
KNOWN ISSUES / BUGS
5 issue(s) documented during testing
# | Severity | Module | Category | Description | Expected Behavior | Actual Behavior | Test Ref | Status
1 | High | Supplier | Validation | Company Name accepts special characters and numbers without any validation. Characters like @#$%^&* are accepted and saved successfully. | Should restrict special characters and show validation error. | CONFIRMED: 'ABC@@ Traders', 'ds&^%##%' saved successfully. | SP-C04, SP-C05, SP-C06 | Confirmed
2 | Medium | Supplier | Validation | No email format validation. Invalid emails like 'notanemail' are accepted without any error on blur or submit. | Should validate email format and show inline error. | Any text accepted without validation. | SP-C09 | Confirmed
3 | Low | Supplier | UI Bug | Phone Number field shows increase/decrease spinner controls (up/down arrows) because the input type is 'number' instead of 'tel' or 'text'. | Should be type=tel or type=text with no spinner controls. | Spinner controls visible — type=number on input. | SP-P06 | Confirmed
4 | Medium | Supplier | Validation | No PAN format validation. PAN should follow Indian format: 5 letters + 4 digits + 1 letter (e.g., ABCDE1234F). Any text is accepted. | Should validate PAN format with regex pattern. | Any text accepted in PAN field. | SP-C10 | Confirmed
5 | High | Supplier | Functionality | No Update button in Edit mode. Only Cancel button is visible in popup-footer. User cannot save edits — Edit mode is non-functional for saving changes. | Update button should appear in edit mode popup-footer right div. | Only Cancel button present. Edit mode is non-functional for saving changes. | SP-E01 | Confirmed